## Sheet 1 - Project Plan
Phase | Session | Description | Time (hrs) | Status | Date | Location
Familiarisation | 1 | Sharon to explain her practice to Tom | 1 | Done |  | Out
| 2 | Tom to explain his practice to Sharon | 1 | Done |  | Out
Output
|  | Document summary of the others role and wider discipline. Homework set by each other that relates to their practice. Recorded Sessions |  | Pending
Research | 1 | Identify and document themes the piece will explore | 2 | Done | 2011-04-11 | Studio
| 2 | Identify themes based on this for the technology to explore | 2 | Done | 2011-04-12 | Studio
Output
Defined list of narrative and technological themes Recorded Sessions
| 3 | Explore and review: Story, The role of the audience, The environment as character, Structure, Creative mapping of project | 7.5 |  | 2011-04-18 | Studio
| 4 | How do you?: Document a narratives thematic & emotive structure, notation to structure and sequence, Define and record a mutual understanding of emotion and feeling | 7.5 |  | 2011-04-20 | Studio
Output
Notes and conclusions Recorded Sessions
| 5 | Critique: Dr Anna Harpin (dramaturg) | 7.5
| 6 | Critique: Tim Atack (music/soundtrack) | 3
Output
Notes and conclusions Recorded Sessions
| 7 | Define and document approach to prototyping/production | 2
Output
Document describing approach a deliverables for final phase
Prototyping | 1 | Script research scene | 30
| 2 | Map narratives thematic and emotive structure identifying key touch points | 3
| 4 | Investigate, prototype and demo different technologies | 30
Output
Single scene Technology prototype / experiments