## Master
ICE ROAD - Raucous - Install 2017
CONSTRUCTION - STRUCTURAL & SET BUILD
| WEEK ONE | [6 empty] | WEEK TWO
| DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
| Mon 21st Aug | Tues 22nd Aug | Weds 23rd Aug | Thurs 24th Aug | Fri 25th Aug | Sat 26th Aug | Sun 27th Aug | 28th August | Tues 29th Aug | Weds 30th Aug | Thurs 31st Aug | Fri 1st Sept | Sat 2nd Sept | Sun 3rd Sept
BANK
PERSONNEL | Builder (tbc) | Builder (tbc) | Builder (tbc) | Builder (tbc) | 3 crew | 3 crew | 3 crew | HOLIDAY | 3 crew | 3 crew | No crew - Creative Team on site | 3 crew | 3 crew | 3 crew
REQS. | WEEK ONE DAY 1: Access to underside of pool needed; WEEK ONE DAY 2: Access to underside of pool needed; WEEK ONE DAY 3: Access to underside of pool needed; WEEK ONE DAY 4: Access to underside of pool needed
EQUIPMENT | bar: WEEK TWO DAY 8
08:00 - 09:00 | Scaffolding support ¦ Wooden structure ¦ Making Good ¦ Snagging ¦ Bar build | Scaffolding support ¦ Wooden structure ¦ Making Good ¦ Snagging ¦ Bar build | Scaffolding support ¦ Wooden structure ¦ Making Good ¦ Snagging ¦ Bar build | Scaffolding support ¦ Wooden structure ¦ Making Good ¦ Snagging ¦ Bar build | Scaffolding support ¦ Wooden structure ¦ Making Good ¦ Snagging ¦ Bar build | Scaffolding support ¦ Wooden structure ¦ Making Good ¦ Snagging ¦ Bar build | Scaffolding support ¦ Wooden structure ¦ Making Good ¦ Snagging ¦ Bar build |  | Scaffolding support ¦ Wooden structure ¦ Making Good ¦ Snagging ¦ Bar build | Scaffolding support ¦ Wooden structure ¦ Making Good ¦ Snagging ¦ Bar build | Sound testing -TIM/KATE/SHARON
09:00 - 10:00 | installed | installed | installed | installed | installed | installed | installed |  | installed | installed |  | Build set | Build set | Build set
10:00 - 11:00 | (structural) | (structural) | (structural) | (structural) | (structural) | (structural) | (structural) |  | (structural) | (structural) |  | (all fixed elements) | (all fixed elements) | (all fixed elements)
11:00 - 12:00 | WEEK TWO DAY 11: Design Meeting - CONOR/ KATE/SHARON
12:00 - 13:00
13:00 - 14:00 | bar: WEEK TWO DAY 8; WEEK TWO DAY 11
14:00 - 15:00
15:00 - 16:00 |  |  |  |  | Install | Install | Install |  | Install | Install | LIMBIC? | Install | Install | Install
16:00 - 17:00 |  |  |  |  | rigging points | rigging points | rigging points |  | rigging points | rigging points | Free for Creative Team TESTING | rigging points | rigging points | rigging points
17:00 - 18:00
18:00 - 19:00
19:00 - 20:00
20:00 - 21:00 | bar: WEEK TWO DAY 8
21:00 - 22:00 | bar: WEEK TWO DAY 8
22:00 - 23:00 | bar: WEEK TWO DAY 8
23:00 - 00:00 | bar: WEEK TWO DAY 8
REHEARSALS & TECH INSTALL | bar: WEEK ONE DAY 1 to WEEK ONE DAY 2
| WEEK THREE | [6 empty] | WEEK FOUR
| DAY 15 | DAY 16 | DAY 17 | DAY 18 | DAY 19 | DAY 20 | DAY 21 | DAY 22 | DAY 23 | DAY 24 | DAY 25 | DAY 26 | DAY 27 | DAY 28
| Mon 4th Sept | Tues 5th Sept | Weds 6th Sept | Thurs 7th Sept | Fri 8th Sept | Sat 9th Sept | Sun 10th Sept | Mon 11th Sept | Tues 12th Sept | Weds 13th Sept | Thurs 14th Sept | Fri 15th Sept | Sat 16th Sept | Sun 17th Sept
| Rehearsals off site | [8 empty] | Rehearsals off site | Rehearsals off site
PERSONNEL | 3 Crew |  |  |  |  | Scenic painters | Scenic painters | Technicians | Technicians | Technicians | Technicians | Technicians | Scenic painters | Scenic painters
REQS.
EQUIPMENT
08:00 - 09:00 | WEEK FOUR DAY 22: Limbic install; WEEK FOUR DAY 23: Limbic install; WEEK FOUR DAY 24: Limbic install; WEEK FOUR DAY 25: Limbic install; WEEK FOUR DAY 26: Limbic install
09:00 - 10:00 | bar: WEEK THREE DAY 15 to WEEK THREE DAY 19; WEEK FOUR DAY 22 to WEEK FOUR DAY 26
10:00 - 11:00 | Build set | Build set | Build set | Build set | Build set | Snow | Snow | Rehearsals | Rehearsals |  |  | Rehearsals | Snow | Snow
11:00 - 12:00 | (all fixed elements) | (all fixed elements) | (all fixed elements) | (all fixed elements) | (all fixed elements) | (contouring & | (contouring & | on site | on site |  |  | on site | (contouring & | (contouring &
12:00 - 13:00 | WEEK THREE DAY 20: scenic painting); WEEK THREE DAY 21: scenic painting); WEEK FOUR DAY 27: scenic painting); WEEK FOUR DAY 28: scenic painting)
13:00 - 14:00 | WEEK FOUR DAY 22: Limbic; WEEK FOUR DAY 23: Limbic; WEEK FOUR DAY 24: Sound install; WEEK FOUR DAY 25: Sound install
14:00 - 15:00
15:00 - 16:00 | WEEK THREE DAY 15: (with Ben & Limbic; WEEK THREE DAY 16: (with Ben & Limbic; WEEK THREE DAY 17: (with Ben & Limbic; WEEK THREE DAY 18: (with Ben & Limbic; WEEK THREE DAY 19: (with Ben & Limbic
16:00 - 17:00 | WEEK THREE DAY 15: marking out lights; WEEK THREE DAY 16: marking out lights; WEEK THREE DAY 17: marking out lights; WEEK THREE DAY 18: marking out lights; WEEK THREE DAY 19: marking out lights
17:00 - 18:00 | WEEK THREE DAY 15: and projectors); WEEK THREE DAY 16: and projectors); WEEK THREE DAY 17: and projectors); WEEK THREE DAY 18: and projectors); WEEK THREE DAY 19: and projectors)
18:00 - 19:00 | WEEK FOUR DAY 22: Limbic install; WEEK FOUR DAY 23: Limbic install; WEEK FOUR DAY 24: Limbic install; WEEK FOUR DAY 25: Limbic install; WEEK FOUR DAY 26: Limbic install
19:00 - 20:00 | bar: WEEK FOUR DAY 22 to WEEK FOUR DAY 26
20:00 - 21:00
21:00 - 22:00
22:00 - 23:00
23:00 - 00:00
REHEARSALS & FINAL TECH INSTALL | WEEK FOUR DAY 22: FULL TECHNICAL REHEARSAL
| WEEK FIVE | [6 empty] | WEEK SIX
| DAY 29 | DAY 30 | DAY 31 | DAY 32 | DAY 33 | DAY 34 | DAY 35 | DAY 36 | DAY 37 | DAY 38 | DAY 39 | DAY 40 | DAY 41 | DAY 42
| Mon 18th Sept | Tues 19th Sept | Weds 20th Sept | Thurs 21st Sept | Fri 22nd Sept | Sat 23rd Sept | Sun 24th Sept | Mon 25th Sept | Tues 26th Sept | Weds 27th Sept | Thurs 28th Sept | Fri 29th Sept | Sat 30th Sept | Sun 1st Oct
PERSONNEL | TSM Leading | TSM Leading | TSM Leading | TSM Leading | TSM Leading | Scenic painters | Entire team | TSM leading | TSM Leading | TSM Leading | TSM Leading | TSM Leading | Entire Team | Entire Team
REQS.
EQUIPMENT
08:00 - 09:00 | Lights/Sound/Video installed | Lights/Sound/Video installed | Lights/Sound/Video installed | Lights/Sound/Video installed | Lights/Sound/Video installed | Snow | Dress bar area | Full tech run | Full tech run | Full tech run | Full tech run | Full tech run | Final prep/stage set | Final prep/stage set
09:00 - 10:00 | WEEK FIVE DAY 29: Limbic cont'd; WEEK FIVE DAY 30: Limbic cont'd; WEEK FIVE DAY 31: Limbic cont'd; WEEK FIVE DAY 32: Limbic cont'd; WEEK FIVE DAY 33: Limbic cont'd; WEEK FIVE DAY 34: (Painting &
10:00 - 11:00 | WEEK FIVE DAY 29: Rehearsals; WEEK FIVE DAY 30: Rehearsals; WEEK FIVE DAY 31: Rehearsals; WEEK FIVE DAY 32: Rehearsals; WEEK FIVE DAY 33: Rehearsals; WEEK FIVE DAY 34: final placement)
11:00 - 12:00
12:00 - 13:00
13:00 - 14:00 | WEEK FIVE DAY 29: Lights; WEEK FIVE DAY 30: Lights; WEEK FIVE DAY 31: Lights; WEEK FIVE DAY 32: Lights; WEEK FIVE DAY 33: Lights
14:00 - 15:00
15:00 - 16:00
16:00 - 17:00
17:00 - 18:00
18:00 - 19:00 | WEEK FIVE DAY 29: Lights; WEEK FIVE DAY 30: Lights; WEEK FIVE DAY 31: Lights; WEEK FIVE DAY 32: Lights; WEEK FIVE DAY 33: Lights
19:00 - 20:00 | WEEK FIVE DAY 29: Projectors; WEEK FIVE DAY 30: Projectors; WEEK FIVE DAY 31: Projectors; WEEK FIVE DAY 32: Projectors; WEEK FIVE DAY 33: Projectors
20:00 - 21:00 | WEEK FIVE DAY 32: Snow; WEEK FIVE DAY 33: Snow
21:00 - 22:00 | WEEK FIVE DAY 32: Painting?; WEEK FIVE DAY 33: Painting?
22:00 - 23:00
23:00 - 00:00
DERIG | bar: WEEK FIVE DAY 29
| WEEK ONE | [6 empty] | WEEK TWO
| DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12
| Mon 21st Nov | Tues 22nd Nov | Weds 23rd Nov | Thurs 24th Nov | Fri 25th Nov | Sat 26th Nov | Sun 27th Nov | Mon 28th Nov | Tues 29th Nov | Weds 30th Nov | Thurs 31st Nov | Fri 1st Dec
LEAD | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER | LEAD PRODUCTION MANAGER
PERSONNEL | TSM | TSM | 3 x Crew | 3 x Crew | 3 x Crew |  |  | 3 x Crew | 3 x Crew | 3 x Crew
REQS.
EQUIPMENT
08:00 - 09:00 | Load out all tech: | Load out all tech: | Strike set | Strike set | Strike set |  |  | Strike set | Strike set | Strike set | Clear space - | Final clean,
09:00 - 10:00 | WEEK ONE DAY 1: Lights; WEEK ONE DAY 2: Lights; WEEK TWO DAY 11: rubbish, recycling; WEEK TWO DAY 12: clear and site
10:00 - 11:00 | WEEK ONE DAY 1: Sound; WEEK ONE DAY 2: Sound; WEEK TWO DAY 11: etc.; WEEK TWO DAY 12: handover
11:00 - 12:00 | WEEK ONE DAY 1: Projectors; WEEK ONE DAY 2: Projectors
12:00 - 13:00 | WEEK ONE DAY 1: Apple tech; WEEK ONE DAY 2: Apple tech
13:00 - 14:00 | bar: WEEK ONE DAY 1 to WEEK ONE DAY 5; WEEK TWO DAY 8 to WEEK TWO DAY 12
14:00 - 15:00 | bar: WEEK ONE DAY 1 to WEEK ONE DAY 5; WEEK TWO DAY 8 to WEEK TWO DAY 12
15:00 - 16:00 | bar: WEEK ONE DAY 1 to WEEK ONE DAY 5; WEEK TWO DAY 8 to WEEK TWO DAY 12
16:00 - 17:00 | bar: WEEK ONE DAY 1 to WEEK ONE DAY 5; WEEK TWO DAY 8 to WEEK TWO DAY 12
17:00 - 18:00 | bar: WEEK ONE DAY 1 to WEEK ONE DAY 5; WEEK TWO DAY 8 to WEEK TWO DAY 12
18:00 - 19:00 | bar: WEEK ONE DAY 1 to WEEK ONE DAY 5; WEEK TWO DAY 8 to WEEK TWO DAY 12
19:00 - 20:00 | bar: WEEK ONE DAY 1 to WEEK ONE DAY 5; WEEK TWO DAY 8 to WEEK TWO DAY 12
20:00 - 21:00
21:00 - 22:00
22:00 - 23:00
23:00 - 00:00

## Schedule
ICE ROAD - PRODUCTION SCHEDULE (DAILY) - JACOBS WELLS BATHS - AUG-NOV 2017
Date | Time | Activity | Personnel | Equipment req. | Notes
Mon 21st Aug
Tues 22nd Aug
Weds 23rd Aug
Thurs 24th Aug
Fri 25th Aug
Sat 26th Aug
Sun 27th Aug
Mon 28th Aug
Tues 29th Aug
Weds 30th Aug
Thurs 31st Aug
Fri 1st Sept
Sat 2nd Sept
Sun 3rd Sept
Mon 4th Sept - 29th Sept

## Staffing
| PRODUCTION MANAGER |  |  |  | ROLE
NO. | DATES (WEEK) | NATURE OF TASK/WORK REQUIRED | No. of days | Cumulative no.
1 | 10 - 14 July | Scoping production needs, scheduling and managing production meetings | 1 | 1 | Sourcing and negotiating deals on wood, scaffolding, steel, snow, gauze, other
2 | 17 - 21 July | sourcing materials, overseeing production budget, booking equipment, | 1 | 2 | - clarify who's responsible for what between the various creative/technical teams
3 | 24 - 28 July | deals with suppliers, transportation etc. | 1 | 3 | Sourcing light and sound equipment to spec - Ben and Tim
4 | 31 July - 4 Aug |  | 1 | 4 | Hold and manage the production budget
5 | 7 - 11 Aug | (Model box and ground plan completed - Conor) | 1 | 5 | Schedule production meetings with team - lead on these
6 | 14 - 18 Aug | (Work on lighting plan begins - Ben) | 1 | 6 | Pull together production teams - technicians, electrician, stage hands etc. (schedule)
7 | 21 - 25 Aug | Load in - scaffolding supports go in | 7 | 13 | Oversee get-out and clear up - schedule everyone accordingly
8 | 28 Aug - 1 Sept | Load in - full set construction / rigging points installed | 7 | 20 | Oversee installation - install to design - set, lighting, sound, projection etc.
9 | 4 - 8 Sept | Rehearsals with cast in space (marking out for lights) | 2 | 22 | Event Plan and Risk Assessments
10 | 11 - 15 Sept | Rehearsals with cast in space (lighting design signed off & ready) | 2 | 24 | Check in during show to ensure everything is running smoothly
11 | 18 - 22 Sept | Rehearsals with cast in space (lights installed ideally) | 2 | 26 | Support Emily with licensing, other venue set up requirements
12 | 25 - 29 Sept | Full technical rehearsal | 4 | 30
13 | 2 - 8 Oct | Previews (2-4 Oct) Press Night (5 Oct) First night (6 Oct) | 0 | 30
14 | 9 - 15 Oct | Shows | 0.2 | 30.2
15 | 16 - 22 Oct | Shows | 0.2 | 30.4
16 | 23 - 29 Oct | Shows | 0.2 | 30.6
17 | 30 Oct - 5 Nov | Shows | 0.2 | 30.8
18 | 6 - 12 Nov | Shows | 0.2 | 31
19 | 13 - 18 Nov | Shows | 0.2 | 31.2
20 | 21 - 25 Nov | De-rig/Get-out | 5 | 36.2
21 | 27 Nov - 1 Dec | De-rig/Get-out (space must be clean/clear by Friday 1st Dec | 4 | 40.2
| TECHNICIANS |  |  |  | ROLE
1 | 11 - 15 Sept | Limbic install | 5 | 5 | Reqs: Good overall technical knowledge, knowledge of QLab
2 | 18 - 22 Sept | Light install (sound?) | 5 | 10 | Installing lights (led by Katy Davies)
3 | 25 - 29 Sept | Full technical rehearsal | 7 | 17 | Installing sound (led by Tim Atak)
4 | 2 - 8 Oct | Previews (2-4 Oct) Press Night (5 Oct) First night (6 Oct) | 7 | 24 | Installing projection equipment (as specified by and supporting Limbic)
5 | 9 - 15 Oct | Shows | 7 | 31 | Installing haze, snow and any other equipment & props/set (led by Production Manager)
6 | 16 - 22 Oct | Shows | 7 | 38 | Operating show
7 | 23 - 29 Oct | Shows | 7 | 45 | Prepping show and resetting space for each performance
8 | 30 Oct - 5 Nov | Shows | 7 | 52 | (overseeing the recharging of totems, topping up snow, returning costumes, general tidying)
9 | 6 - 12 Nov | Shows | 7 | 59
10 | 13 - 18 Nov | Shows | 7 | 66
11 | 21 - 25 Nov | De-rig/Get-out | 2 | 68
| CREW |  |  |  | ROLE
1 | 21 - 25 Aug | Load in - scaffolding supports go in | 6 | 6 | Installing wood, steel, all scenic structures, snow etc.
2 | 28 Aug - 1 Sept | Load in - full set construction / rigging points installed | 6 | 12 | Loading and unloading all equipment
3 | 4 Sept - 1 Oct | Contouring and set dressing (snow) | 4 | 16 | really important
4 | 21 - 25 Nov | De-rig | 5 | 21 | really important
5 | 28 Nov - 1 Dec | De-rig | 5 | 26

## To do list
Notes
Snow - organise placement and removal of (including top-up during run) - advice needed on making it as ridged as possible for durability/retaining shape/recycling etc.
Wooden structures - recycled wood panels from Glastonbury?
Steel ladders/structures - who's supplying?
Cleaners - industrial cleaning for snow removal. Can it be recycled? Advice from supplier on removal.
Recycling of wood, steel and any other disposable materials post show
Crates suspended from overhead rig (may include other materials - rags etc.) - who is sourcing these?
Pea Soup Phantom Hazors + CO2 gas cylinders
Power - existing and supplementing/boosting existing supply - silent generator? Pulling from another source? Someone to test the electrics.
Subwoofers
Dust effect - what and how is it rigged?
Falling snow effect - need to devise system, how to rig etc.
Scaffolding for providing brace support for sprung floor
Wind machines - are these required?
Black out shutters for projectors
Black out of windows in bar area
All light, sound, projectors to run from a tablet - QLab
Board across the top window - on the roofside
Questions
Full floorplan and dimensions needed. Model box to be completed early August
Option to suspend set from steel beams
Weight loading for sprung floor - Structural surveyor
Loadings for overhead rig - Structural surveyor
Loadings for steel beams - Structural surveyor
Storage areas and removal of equipment from space (Storage areas available through Bristol Old Vic/other partners if required)
Cleaning pre-show
Lanterns - are they in storage? Transportation to site. Number and availability.
How much kit needs to be suspended - projectors, set, lights, sound, additional?
Proportion of projection equipment supplied by Limbic vs. local supplier (Bath Spa Uni?)
Projectors could go in earlier depending on the availability of equipment - need to confirm who's supplying
Need to retain playing spaces / space for 60 audience members to move around at ground level
R&D week - HS
Skills and capacity scoping - electrician, stage hands, technicians etc.
Calculate number of days for PM
Key questions for the group -install schedule, equip reqs., crew/technical support

## Personnel
Personnel/Contractors
Name | Role | Responsibilities | Contact number(s) | Contact email
Production Manager
Katy Davies | Head of LX
Technician
Technician
Crew
Crew
Crew
Scenic Painter
Scenic Painter

## Suppliers
MATERIALS | SUPPLIER | DATES | CONTACT
Lights - spec needed
Sound - spec needed
Projectors - spec needed
Snow | Snow Business
Foam and wadding
Gauze
Wood | Glastonbury?
Steel
Scenic paint
Crates, sacks, materials to project onto
Wind machine
Haze machines
Lanterns | Loco Club?
Blackout material - paper/fabric
Costumes - coats, scarves, hats etc. | Charity Shops?
Apples
Power - generator?
Scaffolding
iPad, routers etc. for QLab | Already sourced