## Schedule - Ice Road
5 June | Rewrite script
w/c 12 June | w/c 12 June, Wickham Theatre booked Rehearse and develop a new script with BOV Theatre students | The Wickham | Sharon Clark
15/16 June | Public and private sharing + feedback |  | Sharon Clark
| Feedback from public about draft images and copy for the show |  | Claire Skelcey
| Final short list of actors - availability check |  | Angie Bual + Intern
| Production meeting 3 |  | Dave Wilkie
| Casting / auditions |  | Director + Sharon Clark
2016-06-12 | Contracts issued to cast and stage managers |  | Angie Bual
2016-06-30 | Deadline for final script/ final set design / iteration of tech (hand held) |  | Sharon Clark
2016-06-29 | Production Manager and Producer to make site plan and finalise budget + Production meeting 4 |  | Dave Wilkie
| Meet the church about final set designs, production plans and feedback any concerns |  | Angie + Dave Wilkie
2016-07-10 | Implement revisions on the plan and budget |  | Angie + Dave Wilkie
| Deadline for employing stage managers and technicians |  | Dave Wilkie
2016-07-10 | Pay first round of invoices for creative team (based on design deadlines) |  | Angie Bual
2016-07-17 | Approach drinks sponsor for the launch and press night |  | Angie Bual
2016-07-27 | Production Meeting 5 |  | Dave Wilkie
2016-08-01 | Risk assessment submitted |  | Dave Wilkie
2016-08-21 | Full event plan finalised |  | Dave Wilkie
2016-08-31 | Weekly production meetings begin |  | Dave Wilkie
2016-09-04 | Creative Producer MA Student placement begins (UWE) |  | UWE + Angie Bual
2016-09-04 | Rehearsals |  | Director + Sharon Clark
2016-09-04 | Release rehearsal room shots, quotes from the script and vlogs online |  | Claire Skelcey
2016-09-04 | Print run, and distribution |  | Claire Skelcey
2016-09-11 | Advertise back stage tours |  | Angie Bual
2016-09-18 | Get in |  | Production Manager
2016-09-25 | Tech week |  | Angie Bual
2016-09-25 | Signage installed |  | Claire Skelcey
2016-09-25 | Bar installed |  | Davie Wilkie
2016-10-02 | Previews |  | Angie Bual
2016-10-04 | Press night |  | Angie Bual
2016-10-05 | Special guest night for sponsors, developers |  | Claire Skelcey
2016-10-07 | Release press reviews and update website |  | Claire Skelcey
2016-10-06 | Shows + Back Stage tours |  | Angie Bual
2016-11-21 | Possible Extension |  | Angie Bual
2016-11-27 | Get out |  | Production Manager
2016-12-01 | Feedback, evaluation Box Office & budget reconciliation / Final invoices paid |  | Angie Bual
2016-01-03 | Evaluation |  | Angie Bual

## Sheet 1 - Activity Plan ICE ROA
Activity Plan ICE ROAD
Note
2017-04-03 |  | Application Result | ACE | If we get this in by 31 Dec
2016-04-04 |  | Sharon Clark to begin preparation for R&D including first plot line for the script | Sharon
2016-04-04 | 2016-04-07 | Notify Team of result and confirm availability | Angie Bual
2016-04-04 | 2016-04-07 | Notify partners and venue of result | Angie Bual
2016-04-10 |  | Tom Metcalfe to begin working on the hand held devices for testing at the R&D | Tom Metcalfe
2016-04-10 |  | Employ interns from Bath Spa Uni | Angie Bual
2016-04-10 |  | Apply for theatre and alcohol license for St Thomas’ | Angie Bual
2016-04-10 | 2017-04-13 | Issue contracts to Creative Team | Angie Bual
2016-04-11 |  | Production meeting 1 | Dave Wilkie
2016-04-10 |  | Meeting with Tom Morris regarding director recruitment | Sharon Clark
2016-04-20 |  | Meet directors | Sharon Clark, Angie Bual, Tom Morris
2016-04-24 | 2016-04-24 | Send invitation to VIPS for sharing on 17 May | Angie Bual
2016-05-02 | 2016-05-02 | Casting breakdown sent to Bristol Old Vic Theatre School for R&D | Sharon Clark
2016-05-08 | 2016-05-12 | R&D week with creative team | Sharon Clark | Key date to share with team
2016-05-08 | 2016-05-08 | Full team kick off meeting + Reading of first plot line for the show | Sharon Clark
2016-05-09 | 2016-05-09 | Technology focus with creative technologist. Look at the first iteration of the hand held devices | Tom Metcalfe
2016-05-09 | 2016-05-09 | Site visit to St Thomas and block story onto the space | Sharon Clark
2016-05-10 | 2016-05-10 | Creation of Trailer | Jack Offord
2016-05-10 | 2016-05-10 | Focus on the set and lighting design, and site visit to St Thomas’ | Conor Murphy and Ben Pacey
2016-05-10 | 2016-05-10 | Production Meeting 2 | Dave Wilkie
2016-05-11 |  | Meeting with Laura Mashall, Icon Films, regarding filming projection | Angie, Sharon and Jack
2016-05-12 | 2016-05-12 | Final revised story block. Thoughts on where to develop the script | Sharon Clark
2016-05-15 | 2016-05-15 | Invite audience and guests to R&D showing | Angie Bual
2016-05-17 |  | First consultattion meeting with Nigel Greenhalgh regarding possibility of training arm | Angie & Sharon
2016-05-09 |  | Director's contract to be issued | Angie Bual
2016-05-17 |  | Buy insurance | Angie Bual
2016-05-18 |  | Meet Jack Offord and Limbic and make a plan for the video and projection content + bring Aardman in for consultancy. Then plan the next 3 days of consultant activity. | Angie & Sharon
2016-05-29 | 2016-06-01 | Rehearse and develop a new script with BOV Theatre students | Sharon Clark
2016-06-01 | 2016-06-01 | Public and private sharing + feedback | Sharon Clark | Key date to share with team
2016-06-01 |  | Feedback from public about draft images and copy for the show | Claire Skelcey
2016-06-07 |  | Final short list of actors - availability check | Angie Bual + Intern
2016-06-07 |  | Production meeting 3 | Dave Wilkie
2016-05-26 |  | PR Strategy deadline | Claire Skelcey
2016-06-05 |  | Casting / auditions | Director + Sharon Clark
2016-06-05 |  | Final Copy and print drafts | Claire Skelcey
2016-06-09 | 2016-06-09 | Cast confirmed | Sharon Clark
2016-06-12 | 2016-06-16 | Contracts issued to cast and stage managers | Angie Bual
2016-06-30 |  | Deadline for copy and print sign off | Claire Skelcey
2016-06-30 |  | Deadline for final script | Sharon Clark
2016-06-30 |  | Deadline for final set design | Conor Murphy
2016-06-30 |  | Deadline for next iteration of tech (hand held) | Sharon Clark
2016-06-30 |  | Production Manager and Producer to make site plan and finalise budget | Angie Bual & Dave Wilkie
2016-06-29 |  | Production meeting 4 | Dave Wilkie
2016-07-03 |  | Meet the church about final set designs, production plans and feedback any concerns | Angie + Dave Wilkie
2016-07-10 | 2016-07-14 | Implement revisions on the plan and budget | Angie + Dave Wilkie
|  | Deadline for employing stage managers and technicians | Dave Wilkie
2016-07-10 | 2016-07-14 | Pay first round of invoices for creative team (based on design deadlines) | Angie Bual
2016-07-10 | 2016-07-14
2016-07-17 | 2016-07-21 | Approach drinks sponsor for the launch and press night | Angie Bual
2016-07-27 |  | Production Meeting 5 | Dave Wilkie
2016-08-01 | 2016-08-01 | Tickets on sale | BOV + Watershed
2016-08-01 |  | Risk assessment submitted | Dave Wilkie
2016-08-03 |  | Meeting with church - update plans | Angie Bual
2016-08-21 |  | Full event plan finalised | Dave Wilkie
2016-08-31 |  | Production meeting 5 | Dave Wilkie
2016-09-01 |  | Meeting with Church - update plans | Angie Bual
2016-09-04 |  | Creative Producer MA Student placement begins (UWE) | UWE + Angie Bual
2016-09-04 |  | Ticket and show launch event onsite | Angie Bual
2016-09-04 |  | Website update | Claire Skelcey
2016-09-04 | 2016-09-29 | Rehearsals | Director + Sharon Clark
2016-09-04 | 2016-09-29 | Release rehearsal room shots, quotes from the script and vlogs online | Claire Skelcey
2016-09-04 | 2016-09-29 | Print run, and distribution | Claire Skelcey
7 Sept |  | Production meeting 6 | Dave Wilkie
2016-09-11 |  | Advertise back stage tours | Angie Bual
14 Sept |  | Production meeting 7 | Dave Wilkie
2016-09-18 | 2016-09-22 | Get in | Production Manager
21 Sept |  | Production meeting 8 | Dave Wilkie
2016-09-28 |  | Production meeting 9 | Dave Wilkie
2016-09-25 | 2016-09-29 | Tech week | Angie Bual
2016-09-25 | 2016-09-29 | Signage installed | Claire Skelcey
2016-09-25 | 2016-09-29 | Bar installed | Davie Wilkie
2016-09-29 |  | Portaloos installed | Dave Wilkie
2016-10-02 | 2016-10-03 | Previews | Angie Bual
2016-10-04 |  | Press night | Angie Bual
2016-10-05 |  | Special guest night for sponsors, developers | Claire Skelcey
2016-10-07 |  | Release press reviews and update website | Claire Skelcey
2016-10-06 | 2016-11-18 | Shows + Back Stage tours | Angie Bual
2016-11-21 | 2016-11-25 | Possible Extension | Angie Bual
2016-11-27 | 2016-12-01 | Get out | Production Manager
2016-12-01 | 2016-12-21 | Feedback, evaluation | Angie Bual
2016-12-01 | 2016-12-21 | Box Office reconciliation | Angie Bual
2016-12-01 | 2016-12-21 | Budget reconciliation | Angie Bual
2016-12-01 | 2016-12-21 | Final invoices paid | Angie Bual
2016-12-21 | 2016-01-02 | Christmas break | Angie Bual
2016-01-03 | 2016-01-26 | Evaluation | Angie Bual