## Sheet1
Timeline | Ice Road
2016
October | Historical research (UK desk work)
Commencement of writing funding applications
Meetings with possible partners - RSC and NT
Confirm partnership with Belka
Submit AIDF application for site visit to Leningrad
Confirm venue
November | Write and prepare major bid to trusts and foundations
meet Esmee
AHRC funding submitted with Bath Spa
Technical ‘dreaming’
Draft milestones, key narrative beats, story outline, character analysis,
Submit full ACE application
December | Result of AIDF
Prepare for Leningrad visit
Plan training arm + possible application to Esmee
2017
January | Russian fundraising event - Via crowd funder
February | Visit to St Petersburg
Result full ACE application
Kick off meeting
Publicise crowd funding
March | R&D with the full team. Mapping out the story, first iteration of the design, and developing and integrating technology.
Commence robotics research
Private fundraising
First draft of script complete
April | Production meeting and final design deadline
Commission aromas
Experimentation with hand held technology
Second draft of script
May | Casting
Dedicated studio time for prototyping and testing technology
Build Communications strategy
June | Marketing campaign is finalised
Monthly production meetings begin
Projection mapping build
Robotics
July | Filming for projection
August | Tickets on sale
Trailer on at Watershed
September | Rehearsals begin at Bristol Old Vic
October | Performances
November | Performances + possible extension week
Get out
Finalise payments
December | Wrap up and evaluation
2018
January | Remount
February | London run
March | Moscow run