POSTCARDS FROM CARNEGIE HALL

Dr. Ruth Farrar and Stand + Stare (Lucy Telling & Barney Heywood)

PROPOSED SCHEDULE including a breakdown of our time

| What? | When? | Where? | Who? | Researcher and Artists' time |
| --- | --- | --- | --- | --- |
| RESEARCH |  |  |  |  |
| Preliminary research - Skype with Seamus and/or the archivists - Research via any digitised material, starting with stories suggested by Seamus and CH staff - Begin a list of potential stories and images - Ideas for visuals and plan what we would like to photograph/film at Carnegie Hall |  | Bristol | L + R +B | = 5 days |
| Design: stand/s Initial installation designs inc. materials Recruit fabricator – UK or NYC |  | Bristol | L + B + R | = 1 day |
| Design: app - Meet developer so he can begin basic build Come up with visual identity – image idea, font etc Confirm copy and title of project Create one demo story to test on the app |  | Bristol | L + B + R working with developer | = 4.5 days |
| Planning residency: - Book Air bnb, flights, insurance, check estas etc |  | Bristol | L? | = 1 day |
| Residency at Carnegie Hall In depth research with the archives Additional interviews and atmospheric sound recordings including binaural recordings Long then a short list of potential stories Take photos and video for the visuals Check images with app developer for their image recognition properties as we go Confirm design for the installation on site with Seamus and CH staff Meet a fabricator to make installation in NYC? Confirm any music we can use Discuss signage, graphics, copy etc with CH Discuss web presence on main CH site and any graphics we need to provide for that Test the demo app and discuss with CH |  | Carnegie Hall, NY | L, B + R | = 15 days 7 days away Accommodation for 6 nights Travel |
| PRODUCTION |  |  |  |  |
| Production: stories/content Compile all our research Pin down the ten stories Test main images for image recognition Write scripts if required Record voice over if required Edit audio tracks for all the stories Buy equipment, materials etc for the stand/s Liaise with fabricator (either in Bristol or remotely) Create visuals to illustrate the audio tracks Ensure all credits are correct Work with app developer to ensure that the videos are correctly formatted etc Once AV sequences are completed, send them to developer to incorporate in the app Write and design any signage graphics and send them to CH Graphic design of the postcards |  | Bristol | L, B, R | = 15 days |
| Planning - Plan install at Carnegie Hall, NYC - Write risk assessments/H&S - Travel: book Air bnb, flights, insurance, etc - Schedule for install including getting the stand/s on site (either brought over from UK or by fabricator in NYC) |  | Bristol | L | = 1 day |
| Production: app/online User testing of the app Final designs of the app based on user testing (copy, graphics, user interaction etc) Send app for approval to the app store Finalise content for CH website Finalise printed postcard graphics and send to CH to be printed |  |  | L, R, B | = 2 days |
| INSTALLATION |  |  |  |  |
| Installation Install stand/s in CH Test the stand and the app onsite and make any necessary amendments Staff briefing (provide instructions on how to use) Photograph the stand/s for publicity Film some footage of people using the installation to make into a short promo video (extra) |  |  | B, R | = 1 days work x 2 2 days away Accommodation for 2 nights Travel |
|  |  |  |  | Total inc. installation: 46 days Total not inc. installation: 42 days |